## Setup
Line ref for system
Teams | 4 | 4 | skipsprints
| Product | 300 | 0

## Teams
| PD Sprint 9 | PD Sprint 10 | PD Sprint 11 | PD Sprint 12 | PD Sprint 13
OutOfRangers
Last update | 30/08/2023 11:49:13 | 30/08/2023 11:49:14 | 30/08/2023 11:49:15 | 30/08/2023 11:49:16 | 30/08/2023 11:49:17
Id | 41049 | 41199 | 41303 | 41491 | 41601
State | closed | closed | closed | closed | closed
Start | 19/06/2023 11:06:00 | 03/07/2023 10:51:00 | 17/07/2023 11:33:00 | 31/07/2023 09:33:00 | 14/08/2023 17:06:00
End | 01/07/2023 11:06:00 | 16/07/2023 10:51:00 | 30/07/2023 11:33:00 | 11/08/2023 09:33:00 | 25/08/2023 17:06:00
Name | 2023-S13-OutOfRangers | 2023-S14-OutOfRangers | 2023-S15-OutOfRangers | 2023-S16-OutOfRangers | 2023-S17-OutOfRangers
Issues At Start | 18 | 24 | 17 | 25 | 19
Issues Done | 17 | 36 | 28 | 27 | 37
Stories At Start | 7 | 12 | 6 | 15 | 14
Stories Done | 5 | 13 | 7 | 14 | 12
Bugs total | 9 | 13 | 11 | 13 | 15
bugs Added | 4 | 6 | 9 | 11 | 14
SP at Start | 27 | 36 | 21 | 27 | 30
SP Done | 22 | 36 | 21 | 26 | 30
Issues Not Done | 3 | 6 | 4 | 10 | 5
issues Added | 5 | 18 | 18 | 13 | 28
Issues Removed | 3 | 0 | 3 | 1 | 5
Stories Not Done | 1 | 0 | 0 | 1 | 0
Stories Added | 0 | 1 | 1 | 0 | 0
Stories Removed | 1 | 0 | 0 | 0 | 2
SP Not Done | 5 | 0 | 0 | 1 | 0
SP Added | 0 | 0 | 0 | 0 | 0
Points at Start | 31 | 39 | 27 | 45 | 36
Points Done | 22 | 50 | 30 | 44 | 41
Points Not Done | 5 | 0 | 0 | 1 | 2
Points Added | 0 | 11 | 3 | 0 | 11
Points Removed | 4 | 0 | 0 | 0 | 4
Active Epics | 7 | 12 | 12 | 12 | 11
Sleipnir
Last update | 30/08/2023 11:49:18 | 30/08/2023 11:49:19 | 30/08/2023 11:49:20 | 30/08/2023 11:49:21 | 30/08/2023 11:49:22
Id | 40044 | 40045 | 40695 | 40845 | 41272
State | closed | closed | closed | closed | closed
Start | 19/06/2023 12:00:00 | 03/07/2023 12:00:00 | 17/07/2023 12:00:00 | 31/07/2023 12:00:00 | 14/08/2023 12:00:00
End | 03/07/2023 12:00:00 | 17/07/2023 12:00:00 | 31/07/2023 12:00:00 | 14/08/2023 12:00:00 | 28/08/2023 12:00:00
Name | 2023-S13-Sleipnir | 2023-S14-Sleipnir | 2023-S15-Sleipnir | 2023-S16-Sleipnir | 2023-S17-Sleipnir
Issues At Start | 26 | 34 | 21 | 22 | 19
Issues Done | 6 | 33 | 13 | 10 | 12
Stories At Start | 10 | 8 | 10 | 15 | 13
Stories Done | 4 | 2 | 6 | 5 | 7
Bugs total | 4 | 4 | 5 | 3 | 1
bugs Added | 0 | 0 | 1 | 1 | 0
SP at Start | 41 | 33 | 49 | 64 | 62
SP Done | 13 | 7 | 23 | 16 | 32
Issues Not Done | 20 | 15 | 10 | 13 | 8
issues Added | 2 | 14 | 4 | 1 | 1
Issues Removed | 2 | 0 | 2 | 0 | 0
Stories Not Done | 7 | 6 | 6 | 10 | 7
Stories Added | 1 | 0 | 3 | 0 | 1
Stories Removed | 0 | 0 | 1 | 0 | 0
SP Not Done | 28 | 26 | 26 | 48 | 30
SP Added | 5 | 0 | 3 | 0 | 0
Points at Start | 65 | 81 | 63 | 74 | 66
Points Done | 19 | 63 | 33 | 21 | 39
Points Not Done | 52 | 42 | 34 | 53 | 30
Points Added | 6 | 24 | 9 | 0 | 3
Points Removed | 0 | 0 | 5 | 0 | 0
Active Epics | 10 | 14 | 11 | 8 | 10
Shield
Last update | 30/08/2023 11:49:23 | 30/08/2023 11:49:24 | 30/08/2023 11:49:25 | 30/08/2023 11:49:26 | 30/08/2023 11:49:27
Id | 40820 | 40821 | 40822 | 41421 | 41422
State | closed | closed | closed | closed | closed
Start | 19/06/2023 08:30:00 | 03/07/2023 08:30:00 | 17/07/2023 08:30:00 | 31/07/2023 08:30:00 | 14/08/2023 08:30:00
End | 03/07/2023 08:30:00 | 17/07/2023 08:30:00 | 31/07/2023 08:30:00 | 14/08/2023 08:30:00 | 28/08/2023 08:30:00
Name | 2023-S13-Shield | 2023-S14-Shield | 2023-S15-Shield | 2023-S16-Shield | 2023-S17-Shield
Issues At Start | 13 | 15 | 12 | 13 | 17
Issues Done | 7 | 11 | 7 | 9 | 10
Stories At Start | 8 | 7 | 9 | 10 | 6
Stories Done | 3 | 4 | 5 | 7 | 1
Bugs total | 7 | 5 | 1 | 3 | 3
bugs Added | 4 | 2 | 0 | 2 | 1
SP at Start | 44 | 39 | 35 | 38 | 25
SP Done | 16 | 18 | 21 | 24 | 3
Issues Not Done | 11 | 5 | 6 | 7 | 7
issues Added | 6 | 4 | 2 | 4 | 1
Issues Removed | 1 | 3 | 1 | 1 | 1
Stories Not Done | 5 | 4 | 4 | 3 | 5
Stories Added | 1 | 1 | 1 | 0 | 0
Stories Removed | 1 | 0 | 1 | 0 | 0
SP Not Done | 28 | 21 | 14 | 14 | 22
SP Added | 5 | 0 | 0 | 0 | 0
Points at Start | 44 | 34 | 38 | 38 | 25
Points Done | 16 | 18 | 21 | 24 | 3
Points Not Done | 28 | 21 | 14 | 14 | 22
Points Added | 5 | 5 | 2 | 0 | 0
Points Removed | 5 | 0 | 5 | 0 | 0
Active Epics | 8 | 7 | 7 | 6 | 7
Charizard
Last update | 30/08/2023 11:49:28 | 30/08/2023 11:49:29 | 30/08/2023 11:49:30 | 30/08/2023 11:49:30 | 30/08/2023 11:49:31
Id | 40477 | 40616 | 40650 | 40651 | 40652
State | closed | closed | closed | closed | closed
Start | 19/06/2023 11:28:00 | 03/07/2023 11:14:00 | 17/07/2023 10:25:00 | 31/07/2023 10:26:00 | 14/08/2023 10:26:00
End | 03/07/2023 11:28:00 | 17/07/2023 11:14:00 | 31/07/2023 10:25:00 | 14/08/2023 10:26:00 | 28/08/2023 10:26:00
Name | 2023-S013-Charizard | 2023-S014-Charizard | 2023-S015-Charizard | 2023-S016-Charizard | 2023-S017-Charizard
Issues At Start | 9 | 11 | 6 | 10 | 11
Issues Done | 8 | 11 | 9 | 8 | 9
Stories At Start | 3 | 2 | 3 | 4 | 5
Stories Done | 1 | 2 | 2 | 3 | 3
Bugs total | 0 | 2 | 5 | 2 | 1
bugs Added | 0 | 2 | 5 | 0 | 0
SP at Start | 6 | 7 | 5 | 7 | 13
SP Done | 1 | 7 | 3 | 3 | 8
Issues Not Done | 5 | 4 | 6 | 7 | 5
issues Added | 4 | 4 | 9 | 5 | 3
Issues Removed | 0 | 0 | 0 | 0 | 0
Stories Not Done | 2 | 0 | 1 | 2 | 3
Stories Added | 0 | 0 | 0 | 1 | 1
Stories Removed | 0 | 0 | 0 | 0 | 0
SP Not Done | 5 | 0 | 2 | 4 | 5
SP Added | 0 | 0 | 0 | 1 | 2
Points at Start | 11 | 11 | 7 | 8 | 12
Points Done | 6 | 10 | 4 | 4 | 9
Points Not Done | 7 | 1 | 3 | 5 | 5
Points Added | 2 | 0 | 0 | 1 | 2
Points Removed | 0 | 0 | 0 | 0 | 0
Active Epics | 7 | 7 | 9 | 5 | 7
ACDC
Last update | 30/08/2023 11:49:32 | 30/08/2023 11:49:33 | 30/08/2023 11:49:34 | 30/08/2023 11:49:35 | 30/08/2023 11:49:36
Id | 41085 | 41254 | 41255 | 41256 | 41257
State | closed | closed | closed | closed | active
Start | 21/06/2023 02:43:00 | 06/07/2023 01:55:00 | 21/07/2023 08:21:00 | 07/08/2023 08:23:00 | 18/08/2023 08:23:00
End | 05/07/2023 02:43:00 | 20/07/2023 01:55:00 | 04/08/2023 08:21:00 | 21/08/2023 08:23:00 | 06/09/2023 08:23:00
Name | 2023-S13-SMBO-ACDC | 2023-S14-SMBO-ACDC | 2023-S15-SMBO-ACDC | 2023-S16-SMBO-ACDC | 2023-S17-SMBO-ACDC
Issues At Start | 18 | 27 | 9 | 15 | 15
Issues Done | 5 | 17 | 5 | 12 | 8
Stories At Start | 8 | 17 | 4 | 8 | 5
Stories Done | 2 | 14 | 0 | 5 | 3
Bugs total | 2 | 1 | 4 | 3 | 2
bugs Added | 1 | 0 | 3 | 0 | 0
SP at Start | 23 | 64 | 31 | 49 | 38
SP Done | 2 | 43 | 0 | 20 | 7
Issues Not Done | 18 | 6 | 12 | 7 | 12
issues Added | 6 | 3 | 8 | 4 | 5
Issues Removed | 1 | 7 | 0 | 0 | 0
Stories Not Done | 9 | 4 | 6 | 3 | 5
Stories Added | 3 | 3 | 2 | 0 | 3
Stories Removed | 0 | 2 | 0 | 0 | 0
SP Not Done | 21 | 21 | 31 | 29 | 31
SP Added | 2 | 0 | 5 | 0 | 1
Points at Start | 52 | 82 | 44 | 68 | 52
Points Done | 6 | 44 | 1 | 37 | 16
Points Not Done | 41 | 21 | 49 | 35 | 53
Points Added | 3 | 5 | 6 | 4 | 17
Points Removed | 8 | 22 | 0 | 0 | 0
Active Epics | 14 | 11 | 9 | 10 | 8
Bifrost
Last update | 30/08/2023 11:49:37 | 30/08/2023 11:49:38 | 30/08/2023 11:49:39 | 30/08/2023 11:49:40 | 30/08/2023 11:49:43
Id | 40037 | 40571 | 40703 | 41097 | 41098
State | closed | closed | closed | closed | closed
Start | 19/06/2023 13:00:00 | 03/07/2023 13:00:00 | 17/07/2023 14:00:00 | 31/07/2023 13:00:00 | 16/08/2023 13:00:00
End | 03/07/2023 10:00:00 | 17/07/2023 10:00:00 | 31/07/2023 10:00:00 | 16/08/2023 10:00:00 | 28/08/2023 10:00:00
Name | 2023-S13-Bifrost | 2023-S14-Bifrost | 2023-S15-Bifrost | 2023-S16-Bifrost | 2023-S17-Bifrost
Issues At Start | 27 | 34 | 28 | 27 | 24
Issues Done | 25 | 40 | 29 | 21 | 18
Stories At Start | 13 | 12 | 13 | 12 | 14
Stories Done | 14 | 12 | 11 | 8 | 10
Bugs total | 8 | 13 | 8 | 9 | 4
bugs Added | 5 | 6 | 5 | 5 | 0
SP at Start | 47 | 40 | 48 | 45 | 50
SP Done | 45 | 33 | 40 | 31 | 28
Issues Not Done | 11 | 5 | 4 | 10 | 7
issues Added | 9 | 11 | 6 | 5 | 2
Issues Removed | 0 | 0 | 1 | 1 | 1
Stories Not Done | 1 | 2 | 2 | 4 | 6
Stories Added | 2 | 2 | 0 | 0 | 2
Stories Removed | 0 | 0 | 0 | 0 | 0
SP Not Done | 2 | 7 | 8 | 14 | 22
SP Added | 2 | 0 | 0 | 0 | 0
Points at Start | 59 | 59 | 56 | 83 | 49
Points Done | 58 | 56 | 48 | 35 | 32
Points Not Done | 14 | 9 | 8 | 18 | 22
Points Added | 13 | 6 | 0 | 0 | 5
Points Removed | 0 | 0 | 0 | 30 | 0
Active Epics | 14 | 13 | 13 | 15 | 12
Renegades
Last update | 30/08/2023 11:49:44 | 30/08/2023 11:49:45 | 30/08/2023 11:49:46 | 30/08/2023 11:49:47 | 30/08/2023 11:49:47
Id | 41047 | 41221 | 41443 | 41552 | 41689
State | closed | closed | closed | closed | closed
Start | 19/06/2023 10:00:00 | 03/07/2023 09:06:00 | 17/07/2023 10:00:00 | 31/07/2023 09:42:00 | 14/08/2023 10:00:00
End | 30/06/2023 16:00:00 | 17/07/2023 09:06:00 | 28/07/2023 16:00:00 | 14/08/2023 09:42:00 | 25/08/2023 16:00:00
Name | 2023-S13-Renegades | 2023-S14-Renegades | 2023-S15-Renegades | 2023-S16-Renegades | 2023-S17-Renegades
Issues At Start | 3 | 7 | 10 | 11 | 11
Issues Done | 5 | 2 | 5 | 3 | 7
Stories At Start | 3 | 3 | 6 | 6 | 8
Stories Done | 4 | 1 | 4 | 1 | 3
Bugs total | 1 | 2 | 2 | 1 | 3
bugs Added | 1 | 0 | 1 | 0 | 2
SP at Start | 28 | 17 | 28 | 27 | 26
SP Done | 18 | 5 | 15 | 5 | 18
Issues Not Done | 4 | 8 | 5 | 7 | 5
issues Added | 6 | 3 | 2 | 0 | 5
Issues Removed | 0 | 0 | 2 | 1 | 4
Stories Not Done | 2 | 5 | 3 | 5 | 2
Stories Added | 3 | 3 | 1 | 0 | 0
Stories Removed | 0 | 0 | 0 | 0 | 3
SP Not Done | 10 | 12 | 13 | 22 | 8
SP Added | 0 | 2 | 5 | 0 | 0
Points at Start | 18 | 15 | 23 | 30 | 41
Points Done | 18 | 5 | 15 | 7 | 19
Points Not Done | 10 | 12 | 13 | 23 | 8
Points Added | 10 | 2 | 5 | 0 | 0
Points Removed | 0 | 0 | 0 | 0 | 14
Active Epics | 6 | 6 | 6 | 6 | 9
Hyperion
Last update | 30/08/2023 11:49:48 | 30/08/2023 11:49:49 | 30/08/2023 11:49:50 | 30/08/2023 11:49:51 | 30/08/2023 11:49:51
Id | 40377 | 40767 | 40892 | 41056 | 41226
State | closed | closed | closed | closed | closed
Start | 19/06/2023 16:28:00 | 03/07/2023 14:32:00 | 17/07/2023 12:56:00 | 31/07/2023 16:37:00 | 14/08/2023 12:36:00
End | 03/07/2023 16:28:00 | 17/07/2023 14:32:00 | 31/07/2023 12:56:00 | 14/08/2023 16:37:00 | 28/08/2023 12:36:00
Name | 2023-S13-Hyperion | 2023-S14-Hyperion | 2023-S15-Hyperion | 2023-S16-Hyperion | 2023-Q3-S17-Hyperion
Issues At Start | 8 | 10 | 5 | 12 | 7
Issues Done | 2 | 8 | 4 | 11 | 5
Stories At Start | 5 | 4 | 2 | 4 | 3
Stories Done | 1 | 3 | 0 | 4 | 3
Bugs total | 0 | 2 | 3 | 4 | 0
bugs Added | 0 | 0 | 3 | 1 | 0
SP at Start | 0 | 2 | 0 | 5 | 9
SP Done | 0 | 2 | 0 | 5 | 9
Issues Not Done | 0 | 0 | 0 | 0 | 0
issues Added | 0 | 2 | 3 | 2 | 0
Issues Removed | 6 | 4 | 4 | 3 | 2
Stories Not Done | 0 | 0 | 0 | 0 | 0
Stories Added | 0 | 0 | 0 | 0 | 0
Stories Removed | 4 | 1 | 2 | 0 | 0
SP Not Done | 0 | 0 | 0 | 0 | 0
SP Added | 0 | 0 | 0 | 0 | 0
Points at Start | 18 | 7 | 8 | 13 | 15
Points Done | 0 | 2 | 0 | 9 | 12
Points Not Done | 0 | 0 | 0 | 0 | 0
Points Added | 0 | 0 | 0 | 2 | 0
Points Removed | 18 | 5 | 8 | 6 | 3
Active Epics | 2 | 6 | 2 | 4 | 4
Voyager
Last update | 30/08/2023 11:49:52 | 30/08/2023 11:49:53 | 30/08/2023 11:49:54 | 30/08/2023 11:49:55 | 30/08/2023 11:49:56
Id | 40905 | 41045 | 41129 | 41516 | 41594
State | closed | closed | closed | closed | closed
Start | 19/06/2023 10:00:00 | 03/07/2023 08:00:00 | 17/07/2023 08:20:00 | 31/07/2023 10:00:00 | 14/08/2023 10:00:00
End | 30/06/2023 16:00:00 | 14/07/2023 17:00:00 | 28/07/2023 16:20:00 | 11/08/2023 16:00:00 | 25/08/2023 16:00:00
Name | 2023-S13-Voyager | 2023-S14-Voyager | 2023-S15-Voyager | 2023-S16-Voyager | 2023-S17-Voyager
Issues At Start | 5 | 7 | 13 | 11 | 8
Issues Done | 3 | 3 | 13 | 8 | 5
Stories At Start | 3 | 6 | 4 | 2 | 3
Stories Done | 0 | 2 | 4 | 1 | 3
Bugs total | 0 | 2 | 1 | 2 | 1
bugs Added | 0 | 2 | 0 | 2 | 0
SP at Start | 34 | 31 | 26 | 16 | 26
SP Done | 0 | 8 | 23 | 3 | 18
Issues Not Done | 7 | 9 | 4 | 5 | 6
issues Added | 5 | 7 | 8 | 6 | 3
Issues Removed | 0 | 2 | 4 | 4 | 0
Stories Not Done | 6 | 4 | 1 | 2 | 1
Stories Added | 3 | 1 | 1 | 1 | 1
Stories Removed | 0 | 1 | 0 | 0 | 0
SP Not Done | 34 | 23 | 3 | 13 | 8
SP Added | 16 | 0 | 3 | 5 | 8
Points at Start | 18 | 34 | 23 | 16 | 18
Points Done | 2 | 8 | 23 | 3 | 18
Points Not Done | 34 | 23 | 3 | 13 | 8
Points Added | 18 | 0 | 3 | 5 | 8
Points Removed | 0 | 3 | 0 | 5 | 0
Active Epics | 6 | 7 | 6 | 6 | 5
Metallica
Last update | 30/08/2023 11:49:56 | 30/08/2023 11:49:57 | 30/08/2023 11:49:58 | 30/08/2023 11:49:58
Id | 40858 | 41134 | 41135 | 41218
State | closed | closed | closed | active
Start | 21/06/2023 06:06:00 | 05/07/2023 04:33:00 | 26/07/2023 04:33:00 | 16/08/2023 04:25:00
End | 05/07/2023 06:06:00 | 26/07/2023 04:33:00 | 16/08/2023 04:33:00 | 06/09/2023 04:25:00
Name | 2023-S13-SMBO-Metallica | 2023-S14-SMBO-Metallica | 2023-S15-SMBO-Metallica | 2023-S16-SMBO-Metallica
Issues At Start | 2 | 6 | 7 | 13
Issues Done | 1 | 6 | 8 | 7
Stories At Start | 0 | 4 | 3 | 6
Stories Done | 1 | 3 | 2 | 2
Bugs total | 2 | 2 | 1 | 0
bugs Added | 0 | 0 | 1 | 0
SP at Start | 1 | 13 | 26 | 30
SP Done | 1 | 8 | 18 | 10
Issues Not Done | 3 | 1 | 1 | 8
issues Added | 2 | 1 | 2 | 2
Issues Removed | 0 | 0 | 0 | 0
Stories Not Done | 1 | 1 | 1 | 4
Stories Added | 2 | 0 | 0 | 0
Stories Removed | 0 | 0 | 0 | 0
SP Not Done | 0 | 5 | 8 | 20
SP Added | 0 | 0 | 0 | 0
Points at Start | 3 | 16 | 31 | 44
Points Done | 1 | 11 | 28 | 14
Points Not Done | 3 | 5 | 8 | 30
Points Added | 1 | 0 | 5 | 0
Points Removed | 0 | 0 | 0 | 0
Active Epics | 2 | 2 | 2 | 4
Expendables
Last update | 30/08/2023 11:49:59 | 30/08/2023 11:50:00 | 30/08/2023 11:50:01 | 30/08/2023 11:50:01 | 30/08/2023 11:50:02
Id | 40934 | 41201 | 41420 | 41434 | 41551
State | closed | closed | closed | closed | active
Start | 19/06/2023 11:34:00 | 03/07/2023 12:10:00 | 17/07/2023 09:47:00 | 31/07/2023 14:26:00 | 14/08/2023 00:04:00
End | 03/07/2023 11:34:00 | 17/07/2023 12:10:00 | 31/07/2023 09:47:00 | 14/08/2023 14:26:00 | 28/08/2023 00:04:00
Name | 2023-S13-Expendables | 2023-S14-Expendables | 2023-S15-Expendables | 2023-S16-Expendables | 2023-S17-Expendables
Issues At Start | 4 | 4 | 6 | 8 | 7
Issues Done | 6 | 5 | 7 | 11 | 7
Stories At Start | 4 | 4 | 4 | 8 | 4
Stories Done | 4 | 5 | 4 | 8 | 4
Bugs total | 1 | 0 | 2 | 1 | 1
bugs Added | 1 | 0 | 1 | 1 | 0
SP at Start | 290 | 160 | 160 | 190 | 230
SP Done | 290 | 110 | 160 | 110 | 200
Issues Not Done | 0 | 1 | 0 | 2 | 1
issues Added | 2 | 2 | 1 | 5 | 1
Issues Removed | 0 | 0 | 0 | 0 | 0
Stories Not Done | 0 | 1 | 0 | 2 | 1
Stories Added | 0 | 2 | 0 | 2 | 1
Stories Removed | 0 | 0 | 0 | 0 | 0
SP Not Done | 0 | 50 | 0 | 80 | 30
SP Added | 0 | 0 | 0 | 0 | 0
Points at Start | 290 | 120 | 170 | 180 | 230
Points Done | 300 | 110 | 170 | 130 | 220
Points Not Done | 0 | 50 | 0 | 80 | 30
Points Added | 10 | 40 | 0 | 30 | 20
Points Removed | 0 | 0 | 0 | 0 | 0
Active Epics | 4 | 4 | 3 | 8 | 4
Yggdrasil
Last update | 30/08/2023 11:50:03 | 30/08/2023 11:50:04 | 30/08/2023 11:50:05 | 30/08/2023 11:50:05 | 30/08/2023 11:50:06
Id | 40919 | 41067 | 41200 | 41417 | 41553
State | closed | closed | closed | closed | closed
Start | 19/06/2023 11:22:00 | 03/07/2023 08:00:00 | 17/07/2023 11:20:00 | 31/07/2023 09:00:00 | 14/08/2023 09:57:00
End | 30/06/2023 17:22:00 | 14/07/2023 17:00:00 | 28/07/2023 17:00:00 | 11/08/2023 17:00:00 | 28/08/2023 09:57:00
Name | 2023-S13-Yggdrasil | 2023-S14-Yggdrasil | 2023-S15-Yggdrasil | 2023-S16-Yggdrasil | 2023-S17-Yggdrasil
Issues At Start | 11 | 12 | 17 | 7 | 10
Issues Done | 15 | 26 | 27 | 5 | 9
Stories At Start | 7 | 10 | 9 | 6 | 9
Stories Done | 7 | 13 | 11 | 4 | 6
Bugs total | 2 | 0 | 5 | 0 | 0
bugs Added | 0 | 0 | 1 | 0 | 0
SP at Start | 28 | 37 | 19 | 8 | 18
SP Done | 23 | 34 | 19 | 8 | 18
Issues Not Done | 2 | 1 | 0 | 0 | 0
issues Added | 6 | 16 | 12 | 1 | 4
Issues Removed | 0 | 1 | 2 | 3 | 5
Stories Not Done | 2 | 1 | 0 | 0 | 0
Stories Added | 2 | 5 | 4 | 1 | 2
Stories Removed | 0 | 1 | 2 | 3 | 5
SP Not Done | 5 | 3 | 0 | 0 | 0
SP Added | 0 | 0 | 0 | 0 | 0
Points at Start | 28 | 32 | 22 | 14 | 25
Points Done | 25 | 34 | 23 | 8 | 18
Points Not Done | 5 | 3 | 0 | 0 | 0
Points Added | 2 | 8 | 7 | 2 | 5
Points Removed | 0 | 3 | 6 | 8 | 12
Active Epics | 0 | 0 | 0 | 0 | 0
Ymir
Last update | 30/08/2023 11:50:07 | 30/08/2023 11:50:07 | 30/08/2023 11:50:08 | 30/08/2023 11:50:09 | 30/08/2023 11:50:09
Id | 40878 | 41052 | 41204 | 41384 | 41430
State | closed | closed | closed | closed | closed
Start | 19/06/2023 15:00:00 | 03/07/2023 10:35:00 | 17/07/2023 09:00:00 | 31/07/2023 10:31:00 | 16/08/2023 10:36:00
End | 30/06/2023 23:00:00 | 14/07/2023 18:35:00 | 28/07/2023 17:00:00 | 11/08/2023 18:31:00 | 27/08/2023 18:36:00
Name | 2023-S13-Ymir | 2023-S14-Ymir | 2023-S15-Ymir | 2023-S16-Ymir | 2023-S17-Ymir
Issues At Start | 12 | 11 | 11 | 11 | 10
Issues Done | 5 | 11 | 14 | 8 | 7
Stories At Start | 6 | 4 | 7 | 8 | 8
Stories Done | 4 | 3 | 6 | 6 | 5
Bugs total | 2 | 2 | 3 | 1 | 2
bugs Added | 1 | 0 | 3 | 0 | 1
SP at Start | 38 | 24 | 50 | 29 | 46
SP Done | 28 | 21 | 35 | 22 | 20
Issues Not Done | 9 | 4 | 3 | 3 | 5
issues Added | 2 | 5 | 7 | 0 | 2
Issues Removed | 0 | 1 | 1 | 0 | 0
Stories Not Done | 3 | 1 | 2 | 2 | 4
Stories Added | 1 | 1 | 2 | 0 | 1
Stories Removed | 0 | 1 | 1 | 0 | 0
SP Not Done | 10 | 3 | 15 | 7 | 26
SP Added | 0 | 3 | 13 | 0 | 0
Points at Start | 46 | 47 | 46 | 45 | 48
Points Done | 36 | 45 | 49 | 33 | 23
Points Not Done | 20 | 3 | 20 | 12 | 31
Points Added | 10 | 9 | 25 | 0 | 6
Points Removed | 0 | 8 | 2 | 0 | 0
Active Epics | 0 | 0 | 0 | 0 | 0
Wolfpack
Last update | 30/08/2023 11:50:10 | 30/08/2023 11:50:11 | 30/08/2023 11:50:12 | 30/08/2023 11:50:13 | 30/08/2023 11:50:14
Id | 40503 | 40504 | 40883 | 41061 | 41062
State | closed | closed | closed | closed | closed
Start | 19/06/2023 10:00:00 | 03/07/2023 10:00:00 | 17/07/2023 22:00:00 | 31/07/2023 10:00:00 | 14/08/2023 10:00:00
End | 03/07/2023 10:00:00 | 17/07/2023 10:00:00 | 31/07/2023 22:00:00 | 14/08/2023 10:00:00 | 28/08/2023 10:00:00
Name | 2023-S13-Wolfpack | 2023-S14-Wolfpack | 2023-S15-Wolfpack | 2023-S16-Wolfpack | 2023-S17-Wolfpack
Issues At Start | 26 | 21 | 26 | 31 | 33
Issues Done | 13 | 8 | 4 | 3 | 8
Stories At Start | 9 | 4 | 5 | 6 | 6
Stories Done | 5 | 3 | 1 | 0 | 3
Bugs total | 3 | 5 | 7 | 7 | 7
bugs Added | 1 | 2 | 2 | 1 | 0
SP at Start | 7 | 20 | 9 | 10 | 10
SP Done | 4 | 4 | 1 | 0 | 4
Issues Not Done | 15 | 16 | 26 | 27 | 23
issues Added | 3 | 6 | 5 | 3 | 1
Issues Removed | 1 | 3 | 1 | 4 | 3
Stories Not Done | 4 | 2 | 5 | 5 | 2
Stories Added | 0 | 1 | 1 | 0 | 0
Stories Removed | 0 | 0 | 0 | 1 | 1
SP Not Done | 3 | 16 | 8 | 10 | 6
SP Added | 0 | 0 | 0 | 0 | 0
Points at Start | 9 | 18 | 9 | 12 | 22
Points Done | 6 | 4 | 1 | 0 | 7
Points Not Done | 3 | 16 | 8 | 12 | 8
Points Added | 0 | 2 | 0 | 0 | 0
Points Removed | 0 | 0 | 0 | 0 | 7
Active Epics | 11 | 8 | 8 | 8 | 9
Nexus
Last update | 30/08/2023 11:50:15 | 30/08/2023 11:50:16 | 30/08/2023 11:50:17 | 30/08/2023 11:50:18 | 30/08/2023 11:50:18
Id | 40909 | 40990 | 41267 | 41268 | 41463
State | closed | closed | closed | closed | closed
Start | 19/06/2023 17:37:00 | 03/07/2023 15:04:00 | 17/07/2023 13:09:00 | 31/07/2023 13:41:00 | 14/08/2023 11:25:00
End | 03/07/2023 17:37:00 | 17/07/2023 15:04:00 | 31/07/2023 13:09:00 | 14/08/2023 13:41:00 | 28/08/2023 11:25:00
Name | 2023-S13-Nexus | 2023-S14-Nexus | 2023-S15-Nexus | 2023-S16-Nexus | 2023-S17-Nexus
Issues At Start | 9 | 11 | 12 | 14 | 11
Issues Done | 7 | 10 | 12 | 16 | 11
Stories At Start | 2 | 1 | 4 | 1 | 5
Stories Done | 2 | 1 | 3 | 1 | 5
Bugs total | 1 | 2 | 2 | 6 | 1
bugs Added | 0 | 1 | 0 | 4 | 1
SP at Start | 8 | 5 | 3 | 3 | 16
SP Done | 8 | 5 | 3 | 3 | 16
Issues Not Done | 1 | 1 | 2 | 1 | 0
issues Added | 0 | 1 | 2 | 5 | 1
Issues Removed | 1 | 1 | 0 | 2 | 1
Stories Not Done | 0 | 0 | 1 | 0 | 0
Stories Added | 0 | 0 | 0 | 0 | 0
Stories Removed | 0 | 0 | 0 | 0 | 0
SP Not Done | 0 | 0 | 0 | 0 | 0
SP Added | 0 | 0 | 0 | 0 | 0
Points at Start | 8 | 12 | 6 | 8 | 18
Points Done | 8 | 12 | 6 | 8 | 18
Points Not Done | 0 | 0 | 0 | 0 | 0
Points Added | 0 | 0 | 0 | 0 | 0
Points Removed | 0 | 0 | 0 | 0 | 0
Active Epics | 3 | 5 | 6 | 9 | 7
Phoenix
Last update | 30/08/2023 11:50:19 | 30/08/2023 11:50:20 | 30/08/2023 11:50:21 | 30/08/2023 11:50:22 | 30/08/2023 11:50:23
Id | 40847 | 40920 | 41141 | 41142 | 41330
State | closed | closed | closed | closed | closed
Start | 19/06/2023 11:07:00 | 03/07/2023 09:50:00 | 17/07/2023 13:11:00 | 31/07/2023 13:24:00 | 14/08/2023 13:25:00
End | 03/07/2023 11:07:00 | 17/07/2023 09:50:00 | 31/07/2023 13:11:00 | 14/08/2023 13:24:00 | 28/08/2023 13:25:00
Name | 2023-S13-Phoenix | 2023-S14-Phoenix | 2023-S15-Phoenix | 2023-S16-Phoenix | 2023-S17-Phoenix
Issues At Start | 13 | 8 | 9 | 7 | 9
Issues Done | 15 | 11 | 15 | 9 | 8
Stories At Start | 7 | 4 | 3 | 4 | 3
Stories Done | 7 | 6 | 4 | 5 | 1
Bugs total | 5 | 3 | 5 | 0 | 3
bugs Added | 1 | 2 | 4 | 0 | 1
SP at Start | 25 | 34 | 16 | 23 | 15
SP Done | 25 | 34 | 16 | 23 | 5
Issues Not Done | 2 | 2 | 2 | 0 | 2
issues Added | 4 | 5 | 8 | 2 | 1
Issues Removed | 0 | 0 | 0 | 0 | 0
Stories Not Done | 0 | 0 | 0 | 0 | 2
Stories Added | 0 | 2 | 1 | 1 | 0
Stories Removed | 0 | 0 | 0 | 0 | 0
SP Not Done | 0 | 0 | 0 | 0 | 10
SP Added | 0 | 0 | 0 | 0 | 0
Points at Start | 29 | 31 | 24 | 25 | 30
Points Done | 27 | 40 | 28 | 30 | 20
Points Not Done | 2 | 3 | 4 | 0 | 10
Points Added | 0 | 12 | 8 | 5 | 0
Points Removed | 0 | 0 | 0 | 0 | 0
Active Epics | 8 | 7 | 7 | 5 | 6

## Data
Squad | SprintName | Year | Sprint | Issues At Start | Issues Done | Stories At Start | Stories Done | Bugs total | bugs Added | SP at Start | SP Done | Issues Not Done | issues Added | Issues Removed | Stories Not Done | Stories Added | Stories Removed | SP Not Done | SP Added | Points at Start | Points Done | Points Not Done | Points Added | Points Removed | Active Epics
OutOfRangers | 2023-S13-OutOfRangers | 2023 | 13 | 18 | 17 | 7 | 5 | 9 | 4 | 27 | 22 | 3 | 5 | 3 | 1 | 0 | 1 | 5 | 0 | 31 | 22 | 5 | 0 | 4 | 7
OutOfRangers | 2023-S14-OutOfRangers | 2023 | 14 | 24 | 36 | 12 | 13 | 13 | 6 | 36 | 36 | 6 | 18 | 0 | 0 | 1 | 0 | 0 | 0 | 39 | 50 | 0 | 11 | 0 | 12
OutOfRangers | 2023-S15-OutOfRangers | 2023 | 15 | 17 | 28 | 6 | 7 | 11 | 9 | 21 | 21 | 4 | 18 | 3 | 0 | 1 | 0 | 0 | 0 | 27 | 30 | 0 | 3 | 0 | 12
OutOfRangers | 2023-S16-OutOfRangers | 2023 | 16 | 25 | 27 | 15 | 14 | 13 | 11 | 27 | 26 | 10 | 13 | 1 | 1 | 0 | 0 | 1 | 0 | 45 | 44 | 1 | 0 | 0 | 12
OutOfRangers | 2023-S17-OutOfRangers | 2023 | 17 | 19 | 37 | 14 | 12 | 15 | 14 | 30 | 30 | 5 | 28 | 5 | 0 | 0 | 2 | 0 | 0 | 36 | 41 | 2 | 11 | 4 | 11
Sleipnir | 2023-S13-Sleipnir | 2023 | 13 | 26 | 6 | 10 | 4 | 4 | 0 | 41 | 13 | 20 | 2 | 2 | 7 | 1 | 0 | 28 | 5 | 65 | 19 | 52 | 6 | 0 | 10
Sleipnir | 2023-S14-Sleipnir | 2023 | 14 | 34 | 33 | 8 | 2 | 4 | 0 | 33 | 7 | 15 | 14 | 0 | 6 | 0 | 0 | 26 | 0 | 81 | 63 | 42 | 24 | 0 | 14
Sleipnir | 2023-S15-Sleipnir | 2023 | 15 | 21 | 13 | 10 | 6 | 5 | 1 | 49 | 23 | 10 | 4 | 2 | 6 | 3 | 1 | 26 | 3 | 63 | 33 | 34 | 9 | 5 | 11
Sleipnir | 2023-S16-Sleipnir | 2023 | 16 | 22 | 10 | 15 | 5 | 3 | 1 | 64 | 16 | 13 | 1 | 0 | 10 | 0 | 0 | 48 | 0 | 74 | 21 | 53 | 0 | 0 | 8
Sleipnir | 2023-S17-Sleipnir | 2023 | 17 | 19 | 12 | 13 | 7 | 1 | 0 | 62 | 32 | 8 | 1 | 0 | 7 | 1 | 0 | 30 | 0 | 66 | 39 | 30 | 3 | 0 | 10
Shield | 2023-S13-Shield | 2023 | 13 | 13 | 7 | 8 | 3 | 7 | 4 | 44 | 16 | 11 | 6 | 1 | 5 | 1 | 1 | 28 | 5 | 44 | 16 | 28 | 5 | 5 | 8
Shield | 2023-S14-Shield | 2023 | 14 | 15 | 11 | 7 | 4 | 5 | 2 | 39 | 18 | 5 | 4 | 3 | 4 | 1 | 0 | 21 | 0 | 34 | 18 | 21 | 5 | 0 | 7
Shield | 2023-S15-Shield | 2023 | 15 | 12 | 7 | 9 | 5 | 1 | 0 | 35 | 21 | 6 | 2 | 1 | 4 | 1 | 1 | 14 | 0 | 38 | 21 | 14 | 2 | 5 | 7
Shield | 2023-S16-Shield | 2023 | 16 | 13 | 9 | 10 | 7 | 3 | 2 | 38 | 24 | 7 | 4 | 1 | 3 | 0 | 0 | 14 | 0 | 38 | 24 | 14 | 0 | 0 | 6
Shield | 2023-S17-Shield | 2023 | 17 | 17 | 10 | 6 | 1 | 3 | 1 | 25 | 3 | 7 | 1 | 1 | 5 | 0 | 0 | 22 | 0 | 25 | 3 | 22 | 0 | 0 | 7
Charizard | 2023-S013-Charizard | 2023 | 13 | 9 | 8 | 3 | 1 | 0 | 0 | 6 | 1 | 5 | 4 | 0 | 2 | 0 | 0 | 5 | 0 | 11 | 6 | 7 | 2 | 0 | 7
Charizard | 2023-S014-Charizard | 2023 | 14 | 11 | 11 | 2 | 2 | 2 | 2 | 7 | 7 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 10 | 1 | 0 | 0 | 7
Charizard | 2023-S015-Charizard | 2023 | 15 | 6 | 9 | 3 | 2 | 5 | 5 | 5 | 3 | 6 | 9 | 0 | 1 | 0 | 0 | 2 | 0 | 7 | 4 | 3 | 0 | 0 | 9
Charizard | 2023-S016-Charizard | 2023 | 16 | 10 | 8 | 4 | 3 | 2 | 0 | 7 | 3 | 7 | 5 | 0 | 2 | 1 | 0 | 4 | 1 | 8 | 4 | 5 | 1 | 0 | 5
Charizard | 2023-S017-Charizard | 2023 | 17 | 11 | 9 | 5 | 3 | 1 | 0 | 13 | 8 | 5 | 3 | 0 | 3 | 1 | 0 | 5 | 2 | 12 | 9 | 5 | 2 | 0 | 7
ACDC | 2023-S13-SMBO-ACDC | 2023 | 13 | 18 | 5 | 8 | 2 | 2 | 1 | 23 | 2 | 18 | 6 | 1 | 9 | 3 | 0 | 21 | 2 | 52 | 6 | 41 | 3 | 8 | 14
ACDC | 2023-S14-SMBO-ACDC | 2023 | 14 | 27 | 17 | 17 | 14 | 1 | 0 | 64 | 43 | 6 | 3 | 7 | 4 | 3 | 2 | 21 | 0 | 82 | 44 | 21 | 5 | 22 | 11
ACDC | 2023-S15-SMBO-ACDC | 2023 | 15 | 9 | 5 | 4 | 0 | 4 | 3 | 31 | 0 | 12 | 8 | 0 | 6 | 2 | 0 | 31 | 5 | 44 | 1 | 49 | 6 | 0 | 9
ACDC | 2023-S16-SMBO-ACDC | 2023 | 16 | 15 | 12 | 8 | 5 | 3 | 0 | 49 | 20 | 7 | 4 | 0 | 3 | 0 | 0 | 29 | 0 | 68 | 37 | 35 | 4 | 0 | 10
ACDC | 2023-S17-SMBO-ACDC | 2023 | 17 | 15 | 8 | 5 | 3 | 2 | 0 | 38 | 7 | 12 | 5 | 0 | 5 | 3 | 0 | 31 | 1 | 52 | 16 | 53 | 17 | 0 | 8
Bifrost | 2023-S13-Bifrost | 2023 | 13 | 27 | 25 | 13 | 14 | 8 | 5 | 47 | 45 | 11 | 9 | 0 | 1 | 2 | 0 | 2 | 2 | 59 | 58 | 14 | 13 | 0 | 14
Bifrost | 2023-S14-Bifrost | 2023 | 14 | 34 | 40 | 12 | 12 | 13 | 6 | 40 | 33 | 5 | 11 | 0 | 2 | 2 | 0 | 7 | 0 | 59 | 56 | 9 | 6 | 0 | 13
Bifrost | 2023-S15-Bifrost | 2023 | 15 | 28 | 29 | 13 | 11 | 8 | 5 | 48 | 40 | 4 | 6 | 1 | 2 | 0 | 0 | 8 | 0 | 56 | 48 | 8 | 0 | 0 | 13
Bifrost | 2023-S16-Bifrost | 2023 | 16 | 27 | 21 | 12 | 8 | 9 | 5 | 45 | 31 | 10 | 5 | 1 | 4 | 0 | 0 | 14 | 0 | 83 | 35 | 18 | 0 | 30 | 15
Bifrost | 2023-S17-Bifrost | 2023 | 17 | 24 | 18 | 14 | 10 | 4 | 0 | 50 | 28 | 7 | 2 | 1 | 6 | 2 | 0 | 22 | 0 | 49 | 32 | 22 | 5 | 0 | 12
Renegades | 2023-S13-Renegades | 2023 | 13 | 3 | 5 | 3 | 4 | 1 | 1 | 28 | 18 | 4 | 6 | 0 | 2 | 3 | 0 | 10 | 0 | 18 | 18 | 10 | 10 | 0 | 6
Renegades | 2023-S14-Renegades | 2023 | 14 | 7 | 2 | 3 | 1 | 2 | 0 | 17 | 5 | 8 | 3 | 0 | 5 | 3 | 0 | 12 | 2 | 15 | 5 | 12 | 2 | 0 | 6
Renegades | 2023-S15-Renegades | 2023 | 15 | 10 | 5 | 6 | 4 | 2 | 1 | 28 | 15 | 5 | 2 | 2 | 3 | 1 | 0 | 13 | 5 | 23 | 15 | 13 | 5 | 0 | 6
Renegades | 2023-S16-Renegades | 2023 | 16 | 11 | 3 | 6 | 1 | 1 | 0 | 27 | 5 | 7 | 0 | 1 | 5 | 0 | 0 | 22 | 0 | 30 | 7 | 23 | 0 | 0 | 6
Renegades | 2023-S17-Renegades | 2023 | 17 | 11 | 7 | 8 | 3 | 3 | 2 | 26 | 18 | 5 | 5 | 4 | 2 | 0 | 3 | 8 | 0 | 41 | 19 | 8 | 0 | 14 | 9
Hyperion | 2023-S13-Hyperion | 2023 | 13 | 8 | 2 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 4 | 0 | 0 | 18 | 0 | 0 | 0 | 18 | 2
Hyperion | 2023-S14-Hyperion | 2023 | 14 | 10 | 8 | 4 | 3 | 2 | 0 | 2 | 2 | 0 | 2 | 4 | 0 | 0 | 1 | 0 | 0 | 7 | 2 | 0 | 0 | 5 | 6
Hyperion | 2023-S15-Hyperion | 2023 | 15 | 5 | 4 | 2 | 0 | 3 | 3 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 2 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 2
Hyperion | 2023-S16-Hyperion | 2023 | 16 | 12 | 11 | 4 | 4 | 4 | 1 | 5 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 13 | 9 | 0 | 2 | 6 | 4
Hyperion | 2023-Q3-S17-Hyperion | 2023 | 17 | 7 | 5 | 3 | 3 | 0 | 0 | 9 | 9 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 15 | 12 | 0 | 0 | 3 | 4
Voyager | 2023-S13-Voyager | 2023 | 13 | 5 | 3 | 3 | 0 | 0 | 0 | 34 | 0 | 7 | 5 | 0 | 6 | 3 | 0 | 34 | 16 | 18 | 2 | 34 | 18 | 0 | 6
Voyager | 2023-S14-Voyager | 2023 | 14 | 7 | 3 | 6 | 2 | 2 | 2 | 31 | 8 | 9 | 7 | 2 | 4 | 1 | 1 | 23 | 0 | 34 | 8 | 23 | 0 | 3 | 7
Voyager | 2023-S15-Voyager | 2023 | 15 | 13 | 13 | 4 | 4 | 1 | 0 | 26 | 23 | 4 | 8 | 4 | 1 | 1 | 0 | 3 | 3 | 23 | 23 | 3 | 3 | 0 | 6
Voyager | 2023-S16-Voyager | 2023 | 16 | 11 | 8 | 2 | 1 | 2 | 2 | 16 | 3 | 5 | 6 | 4 | 2 | 1 | 0 | 13 | 5 | 16 | 3 | 13 | 5 | 5 | 6
Voyager | 2023-S17-Voyager | 2023 | 17 | 8 | 5 | 3 | 3 | 1 | 0 | 26 | 18 | 6 | 3 | 0 | 1 | 1 | 0 | 8 | 8 | 18 | 18 | 8 | 8 | 0 | 5
Metallica | 2023-S13-SMBO-Metallica | 2023 | 13 | 2 | 1 | 0 | 1 | 2 | 0 | 1 | 1 | 3 | 2 | 0 | 1 | 2 | 0 | 0 | 0 | 3 | 1 | 3 | 1 | 0 | 2
Metallica | 2023-S14-SMBO-Metallica | 2023 | 14 | 6 | 6 | 4 | 3 | 2 | 0 | 13 | 8 | 1 | 1 | 0 | 1 | 0 | 0 | 5 | 0 | 16 | 11 | 5 | 0 | 0 | 2
Metallica | 2023-S15-SMBO-Metallica | 2023 | 15 | 7 | 8 | 3 | 2 | 1 | 1 | 26 | 18 | 1 | 2 | 0 | 1 | 0 | 0 | 8 | 0 | 31 | 28 | 8 | 5 | 0 | 2
Metallica | 2023-S16-SMBO-Metallica | 2023 | 16 | 13 | 7 | 6 | 2 | 0 | 0 | 30 | 10 | 8 | 2 | 0 | 4 | 0 | 0 | 20 | 0 | 44 | 14 | 30 | 0 | 0 | 4
Expendables | 2023-S13-Expendables | 2023 | 13 | 4 | 6 | 4 | 4 | 1 | 1 | 290 | 290 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 300 | 0 | 10 | 0 | 4
Expendables | 2023-S14-Expendables | 2023 | 14 | 4 | 5 | 4 | 5 | 0 | 0 | 160 | 110 | 1 | 2 | 0 | 1 | 2 | 0 | 50 | 0 | 120 | 110 | 50 | 40 | 0 | 4
Expendables | 2023-S15-Expendables | 2023 | 15 | 6 | 7 | 4 | 4 | 2 | 1 | 160 | 160 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 170 | 170 | 0 | 0 | 0 | 3
Expendables | 2023-S16-Expendables | 2023 | 16 | 8 | 11 | 8 | 8 | 1 | 1 | 190 | 110 | 2 | 5 | 0 | 2 | 2 | 0 | 80 | 0 | 180 | 130 | 80 | 30 | 0 | 8
Expendables | 2023-S17-Expendables | 2023 | 17 | 7 | 7 | 4 | 4 | 1 | 0 | 230 | 200 | 1 | 1 | 0 | 1 | 1 | 0 | 30 | 0 | 230 | 220 | 30 | 20 | 0 | 4
Yggdrasil | 2023-S13-Yggdrasil | 2023 | 13 | 11 | 15 | 7 | 7 | 2 | 0 | 28 | 23 | 2 | 6 | 0 | 2 | 2 | 0 | 5 | 0 | 28 | 25 | 5 | 2 | 0 | 0
Yggdrasil | 2023-S14-Yggdrasil | 2023 | 14 | 12 | 26 | 10 | 13 | 0 | 0 | 37 | 34 | 1 | 16 | 1 | 1 | 5 | 1 | 3 | 0 | 32 | 34 | 3 | 8 | 3 | 0
Yggdrasil | 2023-S15-Yggdrasil | 2023 | 15 | 17 | 27 | 9 | 11 | 5 | 1 | 19 | 19 | 0 | 12 | 2 | 0 | 4 | 2 | 0 | 0 | 22 | 23 | 0 | 7 | 6 | 0
Yggdrasil | 2023-S16-Yggdrasil | 2023 | 16 | 7 | 5 | 6 | 4 | 0 | 0 | 8 | 8 | 0 | 1 | 3 | 0 | 1 | 3 | 0 | 0 | 14 | 8 | 0 | 2 | 8 | 0
Yggdrasil | 2023-S17-Yggdrasil | 2023 | 17 | 10 | 9 | 9 | 6 | 0 | 0 | 18 | 18 | 0 | 4 | 5 | 0 | 2 | 5 | 0 | 0 | 25 | 18 | 0 | 5 | 12 | 0
Ymir | 2023-S13-Ymir | 2023 | 13 | 12 | 5 | 6 | 4 | 2 | 1 | 38 | 28 | 9 | 2 | 0 | 3 | 1 | 0 | 10 | 0 | 46 | 36 | 20 | 10 | 0 | 0
Ymir | 2023-S14-Ymir | 2023 | 14 | 11 | 11 | 4 | 3 | 2 | 0 | 24 | 21 | 4 | 5 | 1 | 1 | 1 | 1 | 3 | 3 | 47 | 45 | 3 | 9 | 8 | 0
Ymir | 2023-S15-Ymir | 2023 | 15 | 11 | 14 | 7 | 6 | 3 | 3 | 50 | 35 | 3 | 7 | 1 | 2 | 2 | 1 | 15 | 13 | 46 | 49 | 20 | 25 | 2 | 0
Ymir | 2023-S16-Ymir | 2023 | 16 | 11 | 8 | 8 | 6 | 1 | 0 | 29 | 22 | 3 | 0 | 0 | 2 | 0 | 0 | 7 | 0 | 45 | 33 | 12 | 0 | 0 | 0
Ymir | 2023-S17-Ymir | 2023 | 17 | 10 | 7 | 8 | 5 | 2 | 1 | 46 | 20 | 5 | 2 | 0 | 4 | 1 | 0 | 26 | 0 | 48 | 23 | 31 | 6 | 0 | 0
Wolfpack | 2023-S13-Wolfpack | 2023 | 13 | 26 | 13 | 9 | 5 | 3 | 1 | 7 | 4 | 15 | 3 | 1 | 4 | 0 | 0 | 3 | 0 | 9 | 6 | 3 | 0 | 0 | 11
Wolfpack | 2023-S14-Wolfpack | 2023 | 14 | 21 | 8 | 4 | 3 | 5 | 2 | 20 | 4 | 16 | 6 | 3 | 2 | 1 | 0 | 16 | 0 | 18 | 4 | 16 | 2 | 0 | 8
Wolfpack | 2023-S15-Wolfpack | 2023 | 15 | 26 | 4 | 5 | 1 | 7 | 2 | 9 | 1 | 26 | 5 | 1 | 5 | 1 | 0 | 8 | 0 | 9 | 1 | 8 | 0 | 0 | 8
Wolfpack | 2023-S16-Wolfpack | 2023 | 16 | 31 | 3 | 6 | 0 | 7 | 1 | 10 | 0 | 27 | 3 | 4 | 5 | 0 | 1 | 10 | 0 | 12 | 0 | 12 | 0 | 0 | 8
Wolfpack | 2023-S17-Wolfpack | 2023 | 17 | 33 | 8 | 6 | 3 | 7 | 0 | 10 | 4 | 23 | 1 | 3 | 2 | 0 | 1 | 6 | 0 | 22 | 7 | 8 | 0 | 7 | 9
Nexus | 2023-S13-Nexus | 2023 | 13 | 9 | 7 | 2 | 2 | 1 | 0 | 8 | 8 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 3
Nexus | 2023-S14-Nexus | 2023 | 14 | 11 | 10 | 1 | 1 | 2 | 1 | 5 | 5 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 5
Nexus | 2023-S15-Nexus | 2023 | 15 | 12 | 12 | 4 | 3 | 2 | 0 | 3 | 3 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 6
Nexus | 2023-S16-Nexus | 2023 | 16 | 14 | 16 | 1 | 1 | 6 | 4 | 3 | 3 | 1 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 9
Nexus | 2023-S17-Nexus | 2023 | 17 | 11 | 11 | 5 | 5 | 1 | 1 | 16 | 16 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 7
Phoenix | 2023-S13-Phoenix | 2023 | 13 | 13 | 15 | 7 | 7 | 5 | 1 | 25 | 25 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 27 | 2 | 0 | 0 | 8
Phoenix | 2023-S14-Phoenix | 2023 | 14 | 8 | 11 | 4 | 6 | 3 | 2 | 34 | 34 | 2 | 5 | 0 | 0 | 2 | 0 | 0 | 0 | 31 | 40 | 3 | 12 | 0 | 7
Phoenix | 2023-S15-Phoenix | 2023 | 15 | 9 | 15 | 3 | 4 | 5 | 4 | 16 | 16 | 2 | 8 | 0 | 0 | 1 | 0 | 0 | 0 | 24 | 28 | 4 | 8 | 0 | 7
Phoenix | 2023-S16-Phoenix | 2023 | 16 | 7 | 9 | 4 | 5 | 0 | 0 | 23 | 23 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 25 | 30 | 0 | 5 | 0 | 5
Phoenix | 2023-S17-Phoenix | 2023 | 17 | 9 | 8 | 3 | 1 | 3 | 1 | 15 | 5 | 2 | 1 | 0 | 2 | 0 | 0 | 10 | 0 | 30 | 20 | 10 | 0 | 0 | 6